## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Disha | 2026-08-02 | Department–JobRole relationship was inconsistent, with the Manager role mapped to multiple departments. | Sprint 2 | Disha | Logical | Redesigned the database schema and normalized the relationship. | 2026-08-02 | Closed | Resolved before database implementation.
2 | Saurabh | 2026-08-01 | Project implementation approach required clarification between Machine Learning and RAG-based implementation. | Sprint 1 | Saurabh | Requirement | Discussed the approach with the team and mentor and updated the implementation roadmap. | 2026-08-01 | Closed | Team aligned on the implementation strategy.
3 | Disha | 2026-08-02 | Missing foreign-key relationships were identified during database schema validation. | Sprint 2 | Disha | Logical | Added the required foreign keys and validated multi-table joins. | 2026-08-02 | Closed | Database integrity verified.
4 | Saurabh | 2026-07-31 | Repository initially lacked required project documentation and community health files. | Sprint 1 | Saurabh | Maintainability | Added MIT License, README, contributing guidelines, and required repository files. | 2026-07-31 | Closed | Repository setup completed.
5 | Aishwarya | 2026-08-01 | Dataset contained duplicate records and missing values affecting data quality. | Sprint 3 | Aishwarya | Logical | Removed duplicate records and handled missing values during data cleaning. | 2026-08-01 | Closed | Dataset cleaned successfully.
6 | Aishwarya | 2026-08-02 | Outliers significantly affected numerical feature distributions. | Sprint 3 | Aishwarya | Logical | Applied IQR-based capping to reduce the impact of extreme values. | 2026-08-02 | Closed | Dataset prepared for EDA.
7 | Aishwarya | 2026-08-03 | Redundant and constant columns affected data preprocessing and analysis. | Sprint 3 | Aishwarya | Standards | Removed unnecessary columns before further analysis. | 2026-08-03 | Closed | Dataset prepared for EDA and modeling.
8 | Pratyush | 2026-08-02 | EmployeeNumber join key was dropped during data cleaning, preventing reliable linkage with fact and dimension tables. | Sprint 4 | Pratyush | Logical | Restored EmployeeNumber from the raw dataset and verified row alignment before rebuilding the schema. | 2026-08-03 | Closed | Star schema rebuilt successfully and validated using join queries.
9 | Saurabh | 2026-08-03 | Project implementation approach required further clarification during initial planning. | Sprint 1 | Saurabh | Requirement | Discussed the implementation approach with the mentor and updated the project roadmap. | 2026-08-03 | Closed | Team aligned on the implementation strategy.
10 | Anil | 2026-08-18 | RAG system integration required additional validation to ensure all components worked together correctly. | Sprint 8 | Anil | Integration | Tested the complete RAG workflow and corrected integration issues identified during validation. | 2026-08-23 | closed | RAG workflow validated successfully.
11 | Anil | 2026-08-20 | Issues were identified during RAG Platform functional testing. | Sprint 8 | Anil | Functional | Investigated the identified issues, applied fixes, and performed regression testing. | 2026-08-25 | Closed | Issues resolved and functionality re-tested.
12 | Anil | 2026-08-25 | Final RAG Platform components required verification before finalization. | Sprint 8 | Anil | Functional | Performed final system testing and verified the major RAG platform workflows. | 2026-08-29 | Closed | Platform finalized after successful testing.
13 | Anil | 2026-08-30 | GitHub repository required final synchronization with the completed RAG implementation. | Sprint 8 | Anil | Maintainability | Updated the repository with the finalized RAG implementation and supporting project files. | 2026-08-31 | Closed | Repository updated successfully.
14 | Anil | 2026-09-02 | RAG frontend deployment required validation after deployment configuration. | Sprint 8 | Anil | Deployment | Deployed the RAG frontend on Streamlit and verified application accessibility and functionality. | 2026-09-03 | Closed | Streamlit deployment successfully.
15 | Anil | 2026-09-02 | RAG backend deployment required verification and connectivity testing. | Sprint 8 | Anil | Deployment | Deployed the backend on Render and verified backend availability and application communication. | 2026-09-03 | Closed | Render backend deployment successfully.