## Sprint Backlog New
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 211 | 14 | 20 | 26.5 | 15.5 | 9 | 12.5 | 17.5 | 13 | 10 | 17 | 26 | 12 | 11 | 7
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-001 | T-001 | Project planning, coordination and management | 2026-07-31 | 2026-09-15 | Saurabh | Plan | 3- Completed | 15 | 3 | 2 | 2 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 1
US-002 | T-002 | Create GitHub Organization | 2026-07-31 | 2026-07-31 | Saurabh | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-003 | Create GitHub Repository | 2026-07-31 | 2026-07-31 | Saurabh | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-004 | Invite team members as collaborators | 2026-08-01 | 2026-08-03 | Saurabh | Plan | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-005 | Prepare professional README and documentation | 2026-08-01 | 2026-08-03 | Saurabh | Code | 3- Completed | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-006 | Upload project datasets | 2026-08-01 | 2026-08-02 | Saurabh | Code | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-007 | Add MIT License | 2026-08-02 | 2026-08-04 | Saurabh | Build | 3- Completed | 1.5 | 0 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-008 | Define project roadmap and implementation strategy | 2026-08-01 | 2026-08-05 | Saurabh | Plan | 3- Completed | 14 | 2 | 2 | 1 | 0 | 1 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 2 | 0
US-009 | T-009 | Updated Github Repositry | 2026-08-03 | 2026-08-05 | Saurabh | Documentation | 3- Completed | 3 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | T-024 | Created PowerBI Dashboard Format & setup | 2026-08-07 | 2026-08-27 | Saurabh | Design | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-025 | T-025 | Created Executive Dashboard in PowerBI | 2026-08-07 | 2026-08-27 | Saurabh | Design | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-026 | T-026 | Created Workforce & Demographics Dashboard | 2026-08-08 | 2026-09-01 | Saurabh | Design | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-047 | T-047 | Test the RAG Platform | 2026-08-09 | 2026-09-10 | Saurabh | Test | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-048 | T-048 | Create PPT Format | 2026-08-09 | 2026-09-08 | Saurabh | Documentation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
US-057 | T-057 | Finalize the GitHub Repositry | 2026-08-10 | 2026-09-09 | Saurabh | Build | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 2
US-058 | T-058 | Updated Agile,unit test, defect docs | 2026-08-20 | 2026-09-15 | Saurabh | Documentation | 3- Completed | 9 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4
SPRINT 2 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-049 | T-049 | Update the PPT Slides | 2026-08-11 | 2026-09-08 | Disha | Documentation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0
US-050 | T-050 | Added Charts & Architecture | 2026-08-12 | 2026-09-09 | Disha | Documentation | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 0
US-051 | T-051 | Finalize the PPT Slides | 2026-08-11 | 2026-09-08 | Disha | Documentation | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-052 | T-052 | Contributed in Github Repositry | 2026-08-02 | 2026-08-04 | Disha | Code | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-010 | T-010 | Data Cleaning | 2026-08-01 | 2026-08-02 | Aishwarya | Code | 3- Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-011 | Data Preparation | 2026-08-01 | 2026-08-02 | Aishwarya | Code | 3- Completed | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-012 | Feature Selection | 2026-08-01 | 2026-08-02 | Aishwarya | Code | 3- Completed | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-013 | Data Preprocessing | 2026-08-01 | 2026-08-02 | Aishwarya | Code | 3- Completed | 3 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-014 | Univariate Analysis is performed | 2026-08-02 | 2026-08-02 | Aishwarya | Code | 3- Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-015 | Exploratory Data Analysis | 2026-08-02 | 2026-08-02 | Aishwarya | Code | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-016 | Save the clean dataset | 2026-08-02 | 2026-08-02 | Aishwarya | Build | 3- Completed | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T-017 | Bivariate Analysis | 2026-08-02 | 2026-08-02 | Aishwarya | Test | 3- Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | T-018 | Contributed in Github, & update Repositry | 2026-08-03 | 2026-08-03 | Aishwarya | Code | 3- Completed | 4 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-035 | T-035 | Model Development | 2026-08-21 | 2026-08-28 | Aishwarya | Code | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0
US-036 | T-036 | Model Evaluation | 2026-08-28 | 2026-09-01 | Aishwarya | Code | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
US-037 | T-037 | Prediction & Insights | 2026-08-29 | 2026-09-04 | Aishwarya | Code | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
SPRINT 4 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-019 | T-019 | Restore EmployeeNumber join key from raw dataset | 2026-08-02 | 2026-08-02 | Pratush | Code | 3- Completed | 2.5 | 0 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | T-020 | Design and build star schema (fact/dimension tables) | 2026-08-02 | 2026-08-02 | Pratush | Code | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T-021 | Load structured data into SQLite database | 2026-08-02 | 2026-08-02 | Pratush | Code | 3- Completed | 5 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | T-022 | Validate schema with join queries | 2026-08-02 | 2026-08-02 | Pratush | Code | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | T-023 | Contributed in GitHub Repositry | 2026-08-03 | 2026-08-03 | Pratush | Code | 3- Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-026 | T-026 | Contributed in GitHub Repositry | 2026-08-02 | 2026-08-02 | Sanjivani | Code | 3- Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-027 | T-027 | Import cleaned dataset into Power BI | 2026-08-04 | 2026-08-04 | Sanjivani | Build | 3- Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-028 | T-028 | Create KPI cards using DAX measures | 2026-08-04 | 2026-08-05 | Sanjivani | Build | 3- Completed | 2.5 | 0 | 0 | 0 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-029 | T-029 | Designed Salary & Experience Insights report page | 2026-08-07 | 2026-08-07 | Sanjivani | Design | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-030 | T-030 | Created Experience, Tenure & Compensation visuals | 2026-08-08 | 2026-08-09 | Sanjivani | Build | 3- Completed | 3.5 | 0 | 0 | 0 | 0 | 0 | 1 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-031 | T-031 | Page layout & visual formatting | 2026-08-09 | 2026-08-10 | Sanjivani | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-032 | T-032 | Data Visualization in PowerBI Dashboard | 2026-08-14 | 2026-08-14 | Rithika | Design | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-033 | T-033 | Contributed in GitHub Repositry | 2026-09-09 | 2026-09-09 | Rithika | Code | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-034 | T-034 | Develop Attrition & Employee Insights Page | 2026-08-14 | 2026-08-14 | Rithika | Build | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-053 | T-053 | Contributed in GitHub Repositry | 2026-08-12 | 2026-08-13 | Moulika | Code | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-054 | T-054 | Create Complete Project Report docs | 2026-09-01 | 2026-09-10 | Moulika | Documentation | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
US-055 | T-055 | Added Images & Diagram in Reports | 2026-09-01 | 2026-09-11 | Moulika | Documentation | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 0
US-056 | T-056 | Update & Finalize Project Report docs | 2026-09-01 | 2026-09-12 | Moulika | Documentation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0
SPRINT 8 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-038 | T-038 | Prepare RAG Platform Implementation Plan | 2026-08-10 | 2026-08-11 | Anil | Plan | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-039 | T-039 | Development Roadmap, Strategy & Architecture | 2026-08-11 | 2026-08-13 | Anil | Documentation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-040 | T-040 | Build and Integrate Complete RAG System | 2026-08-15 | 2026-08-18 | Anil | Code | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0
US-041 | T-041 | Validate, Test and Optimize RAG Platform | 2026-08-18 | 2026-08-23 | Anil | Code | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-042 | T-042 | Fix Issues & Perform Final Testing | 2026-08-20 | 2026-08-25 | Anil | Test | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0
US-043 | T-043 | Finalize RAG Platform | 2026-08-23 | 2026-08-29 | Anil | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-044 | T-044 | Update GitHub Repositry | 2026-08-30 | 2026-08-31 | Anil | Build | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
US-045 | T-045 | Deploy RAG Frontend on Streamlit | 2026-09-02 | 2026-09-03 | Anil | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
US-046 | T-046 | Deploy RAG Backend on Render | 2026-09-02 | 2026-09-03 | Anil | Build | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
SPRINT 9 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-000 | T-000 |  |  |  | Thanvika |  | 1- Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-000 | T-000 |  |  |  | Thanvika |  | 1- Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 10 BACKLOG
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Est. Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-000 | T-000 |  |  |  | Phani |  | 1- Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-000 | T-000 |  |  |  | Phani |  | 1- Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Saurabh Kumar: Please enter the dates in either of these formats: 9/15/2026 or 15-Sep-2026
Note on E2: Saurabh Kumar: Please enter the dates in either of these formats: 9/15/2026 or 15-Sep-2026
Note on I3: Saurabh Kumar: This is the total task estimated in hours for all the user stories
Note on J3: Saurabh Kumar: Pending effort hours after completion of day 1 work
Note on K3: Saurabh Kumar: Pending effort hours after completion of day 2 work
Note on L3: Saurabh Kumar: Pending effort hours after completion of day 3 work
Note on M3: Saurabh Kumar: Pending effort hours after completion of day 4 work
Note on N3: Saurabh Kumar: Pending effort hours after completion of day 5 work
Note on O3: Saurabh Kumar: Pending effort hours after completion of day 6 work
Note on P3: Saurabh Kumar: Pending effort hours after completion of day 7 work
Note on Q3: Saurabh Kumar: Pending effort hours after completion of day 8 work
Note on R3: Saurabh Kumar: Pending effort hours after completion of day 9 work
Note on S3: Saurabh Kumar: Pending effort hours after completion of day 10 work
Note on T3: Saurabh Kumar: Pending effort hours after completion of day 11 work
Note on U3: Saurabh Kumar: Pending effort hours after completion of day 12 work
Note on V3: Saurabh Kumar: Pending effort hours after completion of day 13 work
Note on W3: Saurabh Kumar: Pending effort hours after completion of day 14 work
Note on I6: Saurabh Kumar: Don't Fill this Column
Note on D25: Saurabh Kumar: Please enter the dates in either of these formats: 9/15/2026 or 15-Sep-2026
Note on E25: Saurabh Kumar: Please enter the dates in either of these formats: 9/15/2026 or 15-Sep-2026
Note on D27: Saurabh Kumar: Please enter the dates in either of these formats: 9/15/2026 or 15-Sep-2026
Note on E27: Saurabh Kumar: Please enter the dates in either of these formats: 9/15/2026 or 15-Sep-2026

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Take responsibility for project management, including planning, coordination, and progress | MUST HAVE | US-007 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-002 | Create GitHub Organization for project collaboration | MUST HAVE | None | Saurabh | Completed
Sprint 1 | Sprint 1 | US-003 | Create the central GitHub repository for project source code | MUST HAVE | US-001 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-004 | Invite team members as repository collaborators | MUST HAVE | US-002 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-005 | Prepare professional project README with objectives, milestones, and documentation | MUST HAVE | US-002 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-006 | Upload project datasets to GitHub repository | MUST HAVE | US-002 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-007 | Add MIT License to the repository | SHOULD HAVE | US-001 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-009 | Define the overall project roadmap, implementation strategy, and sprint plan | SHOULD HAVE | US-004 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-034 | Create Executive Dashboard in Power BI | SHOULD HAVE | US-004 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-035 | Create Workforce & Demographics Dashboard | SHOULD HAVE | US-004 | Saurabh | Completed
Sprint 1 | Sprint 1 | US-036 | Define RAG Platform roadmap and implementation strategy | MUST HAVE | US-009 | Saurabh | Completed
Sprint 2 | Sprint 2 | US-008 | Analyze HR Workforce & Attrition dataset and confirm distinct values for categorical fields | MUST HAVE | US-005 | Disha | Completed
Sprint 2 | Sprint 2 | US-010 | Design normalized ER diagram for the HR database schema | MUST HAVE | US-006 | Disha | Completed
Sprint 2 | Sprint 2 | US-011 | Identify and fix Department-JobRole relationship issue | MUST HAVE | US-007 | Disha | Completed
Sprint 2 | Sprint 2 | US-012 | Write CREATE TABLE SQL script for the normalized schema | MUST HAVE | US-008 | Disha | Completed
Sprint 2 | Sprint 2 | US-013 | Set up and initialize local SQLite database with full schema | MUST HAVE | US-009 | Disha | Completed
Sprint 2 | Sprint 2 | US-014 | Load and verify sample employee records across linked tables | MUST HAVE | US-010 | Disha | Completed
Sprint 2 | Sprint 2 | US-015 | Test multi-table join queries to validate schema integrity | SHOULD HAVE | US-011 | Disha | Completed
Sprint 2 | Sprint 2 | US-016 | Recreate final ER diagram in dbdiagram.io for documentation and presentation | SHOULD HAVE | US-012 | Disha | Completed
Sprint 2 | Sprint 2 | US-017 | Document schema design decisions and share handoff files with the team | COULD HAVE | US-013 | Disha | Completed
Sprint 3 | Sprint 3 | US-018 | Complete workforce dataset cleaning module | MUST HAVE | US-008 | Aishwarya | Completed
Sprint 3 | Sprint 3 | US-019 | Perform data quality assessment on workforce dataset | MUST HAVE | US-018 | Aishwarya | Completed
Sprint 3 | Sprint 3 | US-020 | Remove redundant and constant columns from dataset | MUST HAVE | US-019 | Aishwarya | Completed
Sprint 3 | Sprint 3 | US-021 | Validate cleaned workforce dataset | SHOULD HAVE | US-020 | Aishwarya | Completed
Sprint 3 | Sprint 3 | US-022 | Perform outlier treatment using IQR capping | MUST HAVE | US-021 | Aishwarya | Completed
Sprint 3 | Sprint 3 | US-023 | Perform exploratory data analysis for workforce trend analysis | SHOULD HAVE | US-022 | Aishwarya | Completed
Sprint 4 | Sprint 4 | US-024 | Build star-schema data integration pipeline and load structured data into SQLite | MUST HAVE | US-023 | Pratyush | Completed
Sprint 5 | Sprint 5 | US-029 | Import cleaned workforce dataset into Power BI | MUST HAVE | US-021 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-030 | Create KPI cards using DAX measures | SHOULD HAVE | US-029 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-031 | Develop Executive Workforce Overview report page | SHOULD HAVE | US-030 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-032 | Create workforce demographic visualizations | SHOULD HAVE | US-031 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-033 | Implement interactive slicers and validate dashboard | SHOULD HAVE | US-032 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-037 | Develop Salary & Experience Insights report page in Power BI | SHOULD HAVE | US-021 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-038 | Create salary, experience & tenure visuals | SHOULD HAVE | US-037 | Sanjivani | Completed
Sprint 5 | Sprint 5 | US-039 | Enhance Salary & Experience Insights report page | SHOULD HAVE | US-038 | Sanjivani | Completed
Sprint 6 | Sprint 6 | US-025 | Import cleaned dataset into Power BI | MUST HAVE | US-020 | Rithika | Completed
Sprint 6 | Sprint 6 | US-026 | Create KPI cards using DAX measures | MUST HAVE | US-025 | Rithika | Completed
Sprint 6 | Sprint 6 | US-027 | Develop employee attrition dashboard | MUST HAVE | US-026 | Rithika | Completed
Sprint 6 | Sprint 6 | US-028 | Format dashboard and validate report | COULD HAVE | US-027 | Rithika | Completed
Sprint 8 | Sprint 8 | US-040 | Prepare RAG Platform implementation plan | MUST HAVE | US-036 | Anil | Completed
Sprint 8 | Sprint 8 | US-041 | Define RAG Platform development roadmap, strategy, and architecture | MUST HAVE | US-040 | Anil | Completed
Sprint 8 | Sprint 8 | US-042 | Build and integrate the complete RAG System | MUST HAVE | US-041 | Anil | Completed
Sprint 8 | Sprint 8 | US-043 | Validate, test, and optimize the RAG Platform | MUST HAVE | US-042 | Anil | Completed
Sprint 8 | Sprint 8 | US-044 | Fix identified issues and perform final system testing | MUST HAVE | US-043 | Anil | Completed
Sprint 8 | Sprint 8 | US-045 | Finalize the RAG Platform implementation | MUST HAVE | US-044 | Anil | Completed
Sprint 8 | Sprint 8 | US-046 | Update and finalize the RAG Platform GitHub repository | SHOULD HAVE | US-045 | Anil | Completed
Sprint 8 | Sprint 8 | US-047 | Deploy the RAG Platform frontend on Streamlit | MUST HAVE | US-045 | Anil | Completed
Sprint 8 | Sprint 8 | US-048 | Deploy the RAG Platform backend on Render | MUST HAVE | US-045 | Anil | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-31 | 2026-08-01 | Saurabh | Start detailed sprint planning and project management | Avoid delaying requirement clarification | Continue maintaining documentation and coordinating the team | Created GitHub organization, repository, roadmap, assigned tasks, and established the collaboration workflow.
2 | Sprint 2 | 2026-08-02 | 2026-08-02 | Disha | Begin implementation of the database and schema design | Avoid making assumptions without validating the dataset | Continue documenting database decisions and testing schema integrity | Completed ER diagram, SQL schema, SQLite database setup, and database validation.
3 | Sprint 3 | 2026-08-01 | 2026-08-02 | Aishwarya | Start advanced EDA and feature engineering | Avoid skipping data validation before analysis | Continue following data cleaning and preprocessing best practices | Completed data cleaning, preprocessing, feature selection, EDA, outlier treatment, and workforce trend analysis.
4 | Sprint 4 | 2026-08-02 | 2026-08-03 | Pratyush | Start validating join keys and row alignment before merging data from multiple sources | Avoid loading data before validating join keys | Continue validating schema integrity after each modification | Restored EmployeeNumber, designed the dimensional schema, loaded structured data into SQLite, and validated join queries.
5 | Sprint 5 | 2026-08-04 | 2026-08-05 | Sanjivani | Start developing the Executive Workforce Overview dashboard and create KPI measures using DAX | Avoid creating visuals without validating DAX calculations and dataset accuracy | Continue enhancing dashboard interactivity and visual consistency | Created Executive Workforce Overview, Salary & Experience Insights, KPI cards, charts, slicers, and formatted report pages.
6 | Sprint 6 | 2026-08-14 | 2026-08-14 | Rithika | Start validating dashboard insights against the underlying workforce data | Avoid adding visuals without checking data accuracy and report consistency | Continue improving dashboard visualization and employee insights | Developed Power BI data visualizations, created the Attrition & Employee Insights page, and contributed updates to the GitHub repository.
7 | Sprint 7 | 2026-09-01 | 2026-09-12 | Moulika | Start structuring project documentation earlier alongside development | Avoid leaving report formatting and supporting diagrams until the final stage | Continue maintaining clear and professional project documentation | Created the complete project report, added relevant images and diagrams, and updated and finalized the project documentation.
8 | Sprint 8 | 2026-08-10 | 2026-09-03 | Anil | Start systematic RAG implementation, integration, and deployment validation | Avoid postponing integration testing and deployment checks until the final stage | Continue iterative testing, issue fixing, and maintaining the deployment environment | Prepared the RAG implementation plan, defined architecture and strategy, built and integrated the complete RAG system, validated and optimized it, fixed issues, finalized the platform, updated the GitHub repository, and deployed the frontend on Streamlit and backend on Render.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | No impediments | Project planning initiated, GitHub Organization and repository created, and initial project structure established.
Sprint 1 | Day 2 | Repository structure and documentation pending. | Prepared README, uploaded project datasets, added MIT License, and invited team collaborators.
Sprint 1 | Day 3 | Project roadmap and task allocation required further clarification. | Defined project roadmap, implementation strategy, sprint plan, and assigned responsibilities to team members.
Sprint 1 | Day 4 | No major impediments. | Updated GitHub repository and reviewed project documentation and collaboration workflow.
Sprint 1 | Day 5 | Dashboard requirements needed clarification. | Planned Power BI dashboard structure and initiated Executive Workforce and Demographics dashboard development.
Sprint 1 | Day 6 | No major impediments. | Continued Power BI dashboard development and reviewed project progress against the sprint plan.
Sprint 1 | Day 7 | RAG implementation requirements needed to be finalized. | Defined the RAG Platform roadmap, implementation strategy, and initial technical direction.
Sprint 1 | Day 8 | No major impediments. | Continued project coordination, documentation, dashboard work, and RAG implementation planning.
Sprint 1 | Day 9 | No major impediments. | Reviewed project progress and updated required project documentation.
Sprint 1 | Day 10 | Presentation structure required preparation. | Prepared the initial PPT format and organized project presentation content.
Sprint 1 | Day 11 | Presentation content required refinement. | Updated PPT content and continued project documentation.
Sprint 1 | Day 12 | No major impediments. | Reviewed project deliverables and finalized pending repository and documentation updates.
Sprint 1 | Day 13 | Final repository updates pending. | Updated GitHub repository and completed required project materials.
Sprint 1 | Day 14 | Final documentation verification required. | Reviewed Agile, unit-test, and defect documentation and completed pending project updates.
Sprint 2 | Day 1 | Dataset and database requirements required clarification. | Analyzed the HR workforce dataset and started database/schema design activities.
Sprint 2 | Day 2 | Relationship issues identified in the database schema. | Investigated Department–JobRole relationship issues and refined the ER design.
Sprint 2 | Day 3 | Schema relationships required validation. | Created and validated the normalized database schema and SQL table definitions.
Sprint 2 | Day 4 | No major impediments. | Initialized the SQLite database and loaded sample employee records.
Sprint 2 | Day 5 | Multi-table relationships required additional validation. | Executed join queries and verified schema integrity across linked tables.
Sprint 2 | Day 6 | Documentation of schema decisions pending. | Recreated the final ER diagram and documented database design decisions.
Sprint 2 | Day 7 | No major impediments. | Shared database handoff files and updated project documentation.
Sprint 3 | Day 1 | Raw dataset required cleaning and validation. | Started workforce dataset cleaning and data quality assessment.
Sprint 3 | Day 2 | Missing, redundant, and inconsistent data required handling. | Performed data preparation, preprocessing, and removal of redundant/constant columns.
Sprint 3 | Day 3 | Feature quality required validation before analysis. | Performed feature selection, univariate analysis, and exploratory analysis.
Sprint 3 | Day 4 | Potential outliers identified. | Performed bivariate analysis and applied appropriate outlier treatment using IQR capping.
Sprint 3 | Day 5 | Cleaned dataset required verification. | Validated the cleaned dataset and saved the processed dataset for further development.
Sprint 3 | Day 6 | No major impediments. | Continued EDA and analyzed workforce trends and relationships.
Sprint 3 | Day 7 | No major impediments. | Reviewed preprocessing and analysis outputs and updated the GitHub repository.
Sprint 4 | Day 1 | EmployeeNumber join key required restoration. | Restored EmployeeNumber from the raw dataset and validated its alignment.
Sprint 4 | Day 2 | Fact and dimension relationships required design. | Designed the star-schema structure with fact and dimension tables.
Sprint 4 | Day 3 | Structured data loading required validation. | Loaded structured data into SQLite and checked data consistency.
Sprint 4 | Day 4 | Join relationships required verification. | Executed join queries and validated schema integrity and row alignment.
Sprint 5 | Day 1 | Cleaned dataset required integration with Power BI. | Imported the cleaned workforce dataset into Power BI.
Sprint 5 | Day 2 | KPI calculations required validation. | Created DAX-based KPI measures and verified calculations.
Sprint 5 | Day 3 | No major impediments. | Designed the Salary & Experience Insights report page and related visualizations.
Sprint 5 | Day 4 | Dashboard visual consistency required refinement. | Created experience, tenure, salary, and compensation visuals.
Sprint 5 | Day 5 | Final report formatting pending. | Applied page layout, visual formatting, and consistency improvements.
Sprint 6 | Day 1 | Dashboard insights required validation against source data. | Reviewed Power BI data visualizations and validated dashboard outputs.
Sprint 6 | Day 2 | No major impediments. | Continued development of employee and attrition insights.
Sprint 6 | Day 3 | Attrition dashboard required final refinement. | Developed and refined the Attrition & Employee Insights page.
Sprint 6 | Day 4 | No major impediments. | Reviewed dashboard visualization and formatting.
Sprint 6 | Day 5 | GitHub contribution required completion. | Updated the GitHub repository with completed dashboard work.
Sprint 7 | Day 1 | Project documentation required consolidation. | Started preparing the complete project report and organized existing project materials.
Sprint 7 | Day 2 | Supporting diagrams and images were pending. | Added relevant images and diagrams to the project report.
Sprint 7 | Day 3 | Report formatting required refinement. | Reviewed report structure, formatting, and content consistency.
Sprint 7 | Day 4 | No major impediments. | Updated and refined project documentation based on the completed project work.
Sprint 7 | Day 5 | Final report review required. | Performed final documentation review and completed pending report updates.
Sprint 8 | Day 1 | RAG Platform implementation requirements required clarification. | Prepared the RAG Platform implementation plan and defined the development approach.
Sprint 8 | Day 2 | RAG architecture and workflow required finalization. | Defined the RAG development roadmap, strategy, architecture, and system workflow.
Sprint 8 | Day 3 | No major impediments. | Reviewed the proposed RAG architecture and prepared for system implementation.
Sprint 8 | Day 4 | RAG components required integration. | Started building and integrating the complete RAG system.
Sprint 8 | Day 5 | System integration required validation. | Continued RAG system development and integration of required components.
Sprint 8 | Day 6 | No major impediments. | Completed major RAG system implementation and prepared the platform for validation.
Sprint 8 | Day 7 | RAG responses and system functionality required testing. | Validated, tested, and optimized the RAG Platform.
Sprint 8 | Day 8 | Issues identified during system testing. | Fixed identified issues and performed additional functional testing.
Sprint 8 | Day 9 | Final system verification required. | Finalized the RAG Platform and completed final testing.
Sprint 8 | Day 10 | GitHub repository required final updates. | Updated and finalized the RAG Platform GitHub repository.
Sprint 8 | Day 11 | Deployment configuration required verification. | Prepared the RAG Platform for production deployment and verified deployment requirements.
Sprint 8 | Day 12 | No major impediments. | Completed final RAG platform updates and integration checks.
Sprint 8 | Day 13 | Frontend deployment pending. | Deployed the RAG Platform frontend on Streamlit and verified its availability.
Sprint 8 | Day 14 | Backend deployment pending. | Deployed the RAG Platform backend on Render and completed deployment verification.